## Sheet1
Objectives of the Study:
| 1. design and develop a web-based educational platform with the following technical features: | [7 empty] | Technical Editor
|  | 1.1. Centralized learning portal with material distribution and task submission. | [6 empty] | Project Manager
|  | 1.2. AI-Powered Quiz Generator with instructor validation and approval controls. | [6 empty] | Systems Programmer
1.3. Automated assessment and grading engine supporting teacher validation.
1.4. Dynamic remedial quiz generator for targeted student intervention.
1.5. Mastery-based learning module with configurable progression locks.
2. test the functionality of the features mentioned above
3. evaluate the system using ISO 25010 standardize evaluation tool
A. I. M. S. (Automated Intervention and Mastery System): A Web-Based Educational Platform with AI-Driven Assessment and Dynamic Remediation
MONTHS |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
WEEKS |  |  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Analysis and Quick Design
| Team Formation & Initial Setup |  | 2026-02-02 | 2026-02-02 | bar: February W1 to February W2
| Brainstorming & Title Formulation |  | 2026-10-02 | 02/23/2026 | bar: February W2 to February W4
| Title Proposal Submission & Title Defense |  | 02/23/2026 | 02/23/2026 | bar: February W4
| Drafting and Submission of Chapter 1 |  | 2026-02-03 | 03/19/2026 | bar: March W1 to March W3
| Initial Beneficiary Meetings & Adviser Acceptance |  | 2026-10-03 | 2026-11-03 | bar: March W2
| Adviser/Instructor Meeting (Scope & Primary Draft Clarification) |  | 03/17/2026 | 03/17/2026 | bar: March W3
| Drafting and Submission of Chapter 2 (RRL) |  | 03/27/2026 | 03/30/2026 | bar: March W3 to April W1
| Demonstrate: Requirements Interview & Skeleton Prototype Presentation to Beneficiary |  | 2026-06-04 | 2026-06-04 | bar: April W2
Phase 2: Prototype Cycle (Build, Demonstrate, Refine)
| Parallel Task: Continuos Beneficiary Communication & Information Gathering |  | 2026-07-04 | 05/17/2026 | bar: April W2 to May W3
Iteration 1:
|  | Build: Initial LMS Portal & AI Quiz Module Prototyping | 03/16/2026 | 2026-06-04 | bar: March W3 to April W2
|  | Build: System Database & Logic Alignment | 2026-07-04 | 04/13/2026 | bar: April W2 to April W3
|  | Demonstrate: 1st Technical Prototype Review with Capstone Adviser | 04/13/2026 | 04/13/2026 | bar: April W3
|  | Refine: Integration of Adviser Feedback & Beneficiary Data | 04/13/2026 | 04/14/2026 | bar: April W3
Iteration 2:
|  | Build: Rebuilding of Prototype & Algorithm Refinement | 04/14/2026 | 04/21/2026 | bar: April W3
|  | Demonstrate: 2nd Technical Prototype Review with Capstone Adviser | 04/22/2026 | 04/22/2026 | bar: April W4
|  | Refine: Integration of Adviser Feedback & Beneficiary Data | 04/22/2026 | 04/23/2026 | bar: April W4
Pre-deployment Planning:
|  |  | 04/24/2026 | 04/30/2026 | bar: April W4
Iteration 3:
|  | Build: Continuous Algorithm Refinement | 2026-01-05 | 05/17/2026 | bar: May W1 to May W3
|  | Demonstrate: Pre-oral, 50-70% System Presentation | 05/18/2026 | 05/20/2026 | bar: May W3
|  | Refine: Secondary Feature Development based on Panel Feedback | 05/21/2026 | 06/15/2026 | bar: May W3 to June W3
Iteration 4:
|  | Build: Internal System Refinement & Bug Fixing | 06/16/2026 | 06/23/2026 | bar: June W3
|  | Demonstrate: 100% System Presentation & Live Web Application Launch | 06/24/2026 | 06/30/2026 | bar: June W4
Concurrent Documentation:
|  | Writing Chapter 3 | 2026-01-04 | 05/13/2026 | bar: April W1 to May W2
Phase 3: Testing
| Execution of Alpha Test Cases (Internal Testing) |  | 2026-01-07 | 07/15/2026 | bar: July W1 to July W3
| Execution of Beta Test Cases (End-user Testing) |  | 07/16/2026 | 07/31/2026 | bar: July W3 to August W1
| ISO 25010 Evaluation & Survey Distribution |  | 2026-01-08 | 08/15/2026 | bar: August W1 to August W3
| Statistical Analysis of Evaluation Results |  | 08/16/2026 | 08/31/2026 | bar: August W3 to September W1
Phase 4: Implementation
| Writing Chapter 4 |  | 2026-01-09 | 09/30/2026 | bar: September W1 to September W4
| Writing Chapter 5 |  | 2026-01-10 | 10/31/2026 | bar: October W1 to October W3
| Final Capstone Defense |  | 2026-01-11 | 11/15/2026 | bar: November W1 to November W2
| Post-Defense Revisions, Hardbinding of Manuscript, System Turnover |  | 11/16/2026 | 11/30/2026 | bar: November W3 to November W4
MONTHS |  |  | Start Date | Start Date | February W1: July; March W1: August; April W1: September; May W1: October; June W1: November
WEEKS |  |  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 3: Testing
| Execution of Alpha Test Cases (Internal Testing) |  | 2026-01-07 | 07/15/2026 | bar: July W1 to July W3
| Execution of Beta Test Cases (End-user Testing) |  | 07/16/2026 | 07/31/2026 | bar: July W3 to August W1
| ISO 25010 Evaluation & Survey Distribution |  | 2026-01-08 | 08/15/2026 | bar: August W1 to August W3
| Statistical Analysis of Evaluation Results |  | 08/16/2026 | 08/31/2026 | bar: August W3 to September W1
Phase 4: Implementation
| Writing Chapter 4 |  | 2026-01-09 | 09/30/2026 | bar: September W1 to September W4
| Writing Chapter 5 |  | 2026-01-10 | 10/31/2026 | bar: October W1 to October W3
| Final Capstone Defense |  | 2026-01-11 | 11/15/2026 | bar: November W1 to November W2
| Post-Defense Revisions, Hardbinding of Manuscript, System Turnover |  | 11/16/2026 | 11/30/2026 | bar: November W3 to November W4