## AIMS Gantt Chart v2
A.I.M.S. (Automated Intervention and Mastery System): A Web-Based Educational Platform with AI-Driven Assessment and Dynamic Remediation
TASK / ACTIVITY |  |  |  | Start Date | End Date | Assigned to | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
WEEKS | [6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Requirements Planning (Completed)
| Team Formation & Initial Setup |  |  | 02/02/2026 | 02/02/2026 | Orbigoso, Sagum, Zambra
↳ Establish team roles, communication protocols, and shared project repository.
| Brainstorming & Title Formulation |  |  | 02/10/2026 | 02/23/2026 | Orbigoso, Sagum, Zambra
↳ Define A.I.M.S. scope, measurable goals, deliverables, and expected outcomes.
| Title Proposal Submission & Title Defense |  |  | 02/23/2026 | 02/23/2026 | Orbigoso, Sagum, Zambra
↳ Secure panel approval to proceed with AI-powered LMS capstone.
Phase 2: User Design & Data Gathering (Completed)
| Drafting and Submission of Chapter 1 |  |  | 03/02/2026 | 03/19/2026 | Orbigoso, Zambra
↳ Document background, problem statement, objectives, and study significance.
| Initial Client Meeting (HNHS) & Adviser Acceptance |  |  | 03/10/2026 | 03/11/2026 | Orbigoso, Sagum, Zambra
↳ Validate teacher pain points and secure formal adviser acceptance.
| Adviser Meeting (Scope & Draft Clarification) |  |  | 03/17/2026 | 03/17/2026 | Orbigoso, Sagum, Zambra
↳ Align all five core module boundaries with adviser standards and expectations.
| Drafting and Submission of Chapter 2 (RRL) |  |  | 03/27/2026 | 03/30/2026 | Orbigoso, Sagum
↳ Establish empirical literature foundation for each of the five A.I.M.S. modules.
| Initial UI/UX Wireframing & Database Design |  |  | 03/16/2026 | 04/06/2026 | Sagum
↳ Produce system architecture (ERD, DFD) and clickable UI prototype.
| Formal Objectives Presentation & Requirements Interview (HNHS) |  |  | 04/06/2026 | 04/06/2026 | Orbigoso, Sagum, Zambra
↳ Collect structured interview data and sample files for Chapter 3.
Phase 3: Rapid Construction (Active: April – June)
| System Database & Backend Logic Setup |  |  | 04/07/2026 | 04/13/2026 | Sagum
↳ Implement Prisma schema, REST API, JWT auth, and multi-school isolation.
| Infrastructure Research & Budget Finalization |  |  | 04/13/2026 | 04/30/2026 | Orbigoso, Sagum, Zambra
↳ Finalize VPS hosting, Gemini API credits, domain cost, and total project budget.
| Core Module: Centralized Digital Library & Course Management |  |  | 04/14/2026 | 04/28/2026 | Sagum
↳ Enable teachers to upload, organize, and distribute lesson modules securely online.
| Core Module: AI-Powered Quiz Generator (Gemini API) |  |  | 04/21/2026 | 05/12/2026 | Sagum
↳ Auto-generate MCQ, T/F, and Essay questions from teacher-uploaded content.
| Core Module: Automated Grading & Customizable Rubric System |  |  | 05/05/2026 | 05/18/2026 | Sagum
↳ Instantly compute scores based on teacher-defined customizable rubrics.
| 50-70% System Presentation |  |  | 05/13/2026 | 05/15/2026 | Orbigoso, Sagum, Zambra
↳ Demonstrate Digital Library, Quiz Generator, and Auto-Grading to panel.
| Writing Chapter 3 (Methodology) |  |  | 05/16/2026 | 05/31/2026 | Orbigoso, Zambra
↳ Document RAD model, instruments, sampling, and ISO 25010 evaluation plan.
| Core Module: Mastery-Lock System & Teacher Dashboard |  |  | 05/16/2026 | 06/15/2026 | Sagum
↳ Build conditional progression engine and real-time teacher dashboard.
| Cross-System Integration (Scheduling & Class Record APIs) |  |  | 06/05/2026 | 06/23/2026 | Sagum
↳ Sync enrollment from partner Scheduling and push partial grades to Class Record.
| Internal System Refinement & Bug Fixing |  |  | 06/16/2026 | 06/23/2026 | Sagum
↳ Resolve all critical bugs and optimize API performance before deployment.
| 100% System Presentation & Live Web Deployment |  |  | 06/24/2026 | 06/30/2026 | Orbigoso, Sagum, Zambra
↳ Deploy production-ready A.I.M.S. to HNHS and demonstrate all five modules.
Phase 4: Testing & Evaluation (July – August)
| Alpha Testing (Internal Team) |  |  | 07/01/2026 | 07/15/2026 | Orbigoso, Sagum, Zambra
↳ Identify and log all functional issues internally before releasing to end-users.
| Beta Testing (HNHS Teachers & Students) |  |  | 07/16/2026 | 07/31/2026 | Orbigoso, Sagum, Zambra
↳ Collect structured feedback from real users on usability and workflow fit.
| ISO 25010 Evaluation Survey Deployment |  |  | 08/01/2026 | 08/15/2026 | Orbigoso, Sagum, Zambra
↳ Evaluate system quality across all 8 ISO 25010 characteristics with respondents.
| Statistical Analysis of Evaluation Results |  |  | 08/16/2026 | 08/31/2026 | Orbigoso, Sagum, Zambra
↳ Compute weighted mean scores, standard deviation, and interpret findings.
Phase 5: Final Documentation & Cutover (September – November)
| Writing Chapter 4 (Results & Discussion) |  |  | 09/01/2026 | 09/30/2026 | Orbigoso, Zambra
↳ Present, analyze, and interpret ISO 25010 evaluation results per quality characteristic.
| Writing Chapter 5 (Conclusion & Recommendations) |  |  | 10/01/2026 | 10/31/2026 | Orbigoso, Zambra
↳ Summarize research contributions, limitations, and propose future enhancements.
| Final Capstone Defense |  |  | 11/01/2026 | 11/15/2026 | Orbigoso, Sagum, Zambra
↳ Successfully defend all five chapters and the A.I.M.S. system to the panel.
| Post-Defense Revisions, Hardbinding & System Turnover |  |  | 11/16/2026 | 11/30/2026 | Orbigoso, Sagum, Zambra
↳ Finalize manuscript, hardbind thesis, and formally transfer A.I.M.S. to HNHS.
Cost Planning:
Location / Phase |  | Expense Description | Quantity |  | Unit Cost (PHP) | Total Cost (PHP) | February W1: Expense Category; March W1: Per Member (3 Members)
Hinigaran - Past (1 Trip) |  | Transportation (Fuel Contribution) | 3 contributions |  | 150 | 450 | February W1: Transportation; March W1: 150
Hinigaran - Past (1 Trip) |  | Pocket Money | 3 members |  | 200 | 600 | February W1: Pocket Money; March W1: 200
Hinigaran - Future (4 Trips) |  | Transportation (Commute) | 12 trips (3 members x 4) |  | 240 | 2880 | February W1: Transportation; March W1: 960
Hinigaran - Future (4 Trips) |  | Pocket Money | 12 trips (3 members x 4) |  | 200 | 2400 | February W1: Pocket Money; March W1: 800
System Hosting (6 Months) |  | VPS Subscription (shared with partner groups) | 6 months |  | 334 | 2004 | February W1: VPS Hosting; March W1: 125.25
AI Services |  | Google Gemini API Credits (estimated) | 6 months |  | 500 | 3000 | February W1: Gemini API; March W1: 1000
Domain Name |  | Annual Domain Registration (.com) | 1 year |  | 600 | 600 | February W1: Domain; March W1: 200
Printing & Documentation |  | Chapter drafts, survey forms & final manuscript | Estimate |  | 1000 | 1000 | February W1: Documentation; March W1: 333.33
GRAND TOTAL | [5 empty] | 12934 | February W1: PHP 3,768.58 per member