## Sheet1
A. T. L. A. S. (Automated Timetabling and Locations Allocation System): A Web-Based Academic Scheduling Application
MONTHS |  |  |  | Start Date | End Date | Assigned to | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
WEEKS | [6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Requirements Planning (Completed)
| Team Formation & Initial Setup |  |  | 2026-02-02 | 2026-02-02 | Curio, Gilera, Gromea | bar: February W1 to February W2
| Brainstorming & Title Formulation |  |  | 2026-10-02 | 02/23/2026 | Curio, Gilera, Gromea | bar: February W2 to February W4
| Title Proposal Submission & Title Defense |  |  | 02/23/2026 | 02/23/2026 | Curio, Gilera, Gromea | bar: February W4
Phase 2: User Design & Data Gathering (Completed)
| Drafting and Submission of Chapter 1 |  |  | 2026-02-03 | 03/19/2026 | Gilera | bar: March W1 to March W3
| Initial Client Meetings (EMEMHS & HNHS) & Adviser Acceptance |  |  | 2026-10-03 | 2026-11-03 | Curio, Gilera, Gromea | bar: March W2
| Adviser/Instructor Meeting (Scope & Primary Draft Clarification) |  |  | 03/17/2026 | 03/17/2026 | Curio, Gilera, Gromea | bar: March W3
| Drafting and Submission of Chapter 2 (RRL) |  |  | 03/27/2026 | 03/30/2026 | Curio, Gilera | bar: March W3 to April W1
| Initial Algorithm & UI Skeleton Prototyping |  |  | 03/16/2026 | 2026-06-04 | Gromea | bar: March W3 to April W2
| Formal Presentation of Objectives & Requirements Interview (EMEMHS) |  |  | 2026-06-04 | 2026-06-04 | Curio, Gilera, Gromea | bar: April W2
Phase 3: Rapid Construction (Active: April – June)
| System Database & Logic Alignment |  |  | 2026-07-04 | 04/13/2026 | Gromea | bar: April W2 to April W3
| Infrastructure Research & Budget Finalization |  |  | 04/13/2026 | 04/30/2026 | Curio, Gilera, Gromea | bar: April W2 to May W1
| Iterative Algorithm Refinement |  |  | 04/14/2026 | 2026-10-05 | Gromea | bar: April W3 to May W3
| 50-70% System Presentation |  |  | 05/13/2026 | 05/15/2026 | Curio, Gilera, Gromea | bar: May W3
| Writing Chapter 3 |  |  | 05/16/2026 | 05/31/2026 | Curio, Gilera | bar: May W3 to May W4
| Secondary Feature Development |  |  | 05/16/2026 | 06/15/2026 | Gromea | bar: May W3 to June W3
| Internal System Refinement & Bug Fixing |  |  | 06/16/2026 | 06/23/2026 | Gromea | bar: June W3 to June W4
| 100% System Presentation & Live Web Deployment |  |  | 06/24/2026 | 06/30/2026 | Curio, Gilera, Gromea | bar: June W4
Phase 4: Testing & Evaluation (July – August)
| Alpha Testing |  |  | 2026-01-07 | 07/15/2026 | Curio, Gilera, Gromea | bar: July W1 to July W3
| Beta Testing |  |  | 07/16/2026 | 07/31/2026 | Curio, Gilera, Gromea | bar: July W3 to August W1
| ISO 25010 Evaluation |  |  | 2026-01-08 | 08/15/2026 | Curio, Gilera, Gromea | bar: August W1 to August W3
| Statistical Analysis of Evaluation Results |  |  | 08/16/2026 | 08/31/2026 | Curio, Gilera, Gromea | bar: August W3 to September W1
Phase 5: Final Documentation & Cutover (September – November)
| Writing Chapter 4 |  |  | 2026-01-09 | 09/30/2026 | Curio, Gilera | bar: September W1 to September W4
| Writing Chapter 5 |  |  | 2026-01-10 | 10/31/2026 | Curio, Gilera | bar: October W1 to October W3
| Final Capstone Defense |  |  | 2026-01-11 | 11/15/2026 | Curio, Gilera, Gromea | bar: November W1 to November W2
| Post-Defense Revisions, Hardbinding of Manuscript, System Turnover |  |  | 11/16/2026 | 11/30/2026 | Curio, Gilera, Gromea | bar: November W3 to November W4
Cost Planning: | [6 empty] | August W1: Roles:
Location / Phase |  | Expense Description | Quantity |  | Unit Cost (PHP) | Total Cost (PHP) | February W1: Expense Category; March W4: Core Member (12 Members); May W2: Additional Member (4 Members); August W2: Curio, Josh Nathan:; September W3: Technical Editor
Hinigaran (Past - 1 Trip) |  | Transportation (Fuel Contribution) | 8 contributions |  | 150 | 1200 | February W1: Hinigaran Transportation; March W4: 1060; May W2: 0; August W2: Gilera, Rowena:; September W3: Project Manager
Hinigaran (Past - 1 Trip) |  | Pocket Money | 12 members |  | 200 | 2400 | February W1: Hinigaran Pocket Money; March W4: 1000; May W2: 0; August W2: Gromea, Nehje John:; September W3: Systems Programmer
Hinigaran (Future - 4 Trips) |  | Transportation (Commute) | 48 individual trips (12x4) |  | 240 | 11520 | February W1: Pulupandan Transportation; March W4: 640; May W2: 640
Hinigaran (Future - 4 Trips) |  | Pocket Money | 48 individual trips (12x4) |  | 200 | 9600 | February W1: Pulupandan Pocket Money; March W4: 800; May W2: 800
Pulupandan (Future - 4 Trips) |  | Transportation (Commute) | 64 individual trips (16x4) |  | 160 | 10240 | February W1: VPS Hosting Share (Split 16 ways); March W4: 125.25; May W2: 125.25
Pulupandan (Future - 4 Trips) |  | Pocket Money | 64 individual trips (16x4) |  | 200 | 12800 | February W1: Total Estimated Cost Per Person; March W4: 3625.25; May W2: 1565.25
System Hosting (6 Months) |  | VPS Subscription | 6 months |  | 334 | 2004
GRAND TOTAL |  | 49764