## AIMS Gantt Chart
AIMS — Automated Intervention and Mastery System ¦ Project Gantt Chart ¦ Feb 2026 – Nov 2026
Task / Activity | Start | End | Status | Feb 2026 |  |  |  | Mar 2026 |  |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  | Jun 2026 |  |  |  | Jul–Aug |  |  |  | Sep 2026 |  |  |  | Oct 2026 |  |  |  | Nov 2026
|  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
3RD YEAR · February – June 2026
1. Planning Phase | Feb 2026 W1 | Feb 2026 W2 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
1.1 Define scope, objectives & team roles | Feb 2026 W1 | Feb 2026 W1 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
1.2 Identify stakeholders & requirements | Feb 2026 W1 | Feb 2026 W2 | ✓ Done | bar: Feb 2026 W1 to Feb 2026 W2
1.3 Select SDLC (RAD) & Gantt Chart | Feb 2026 W2 | Feb 2026 W2 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
1.4 Setup dev environment & repositories | Feb 2026 W2 | Feb 2026 W2 | ✓ Done | bar: Feb 2026 W2
2. Analysis & Design Phase | Feb 2026 W3 | Mar 2026 W2 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
2.1 Gather user & system requirements | Feb 2026 W3 | Feb 2026 W3 | ✓ Done | bar: Feb 2026 W3
2.2 Define system features & user stories | Feb 2026 W3 | Feb 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
2.3 ERD, DFD & system architecture | Feb 2026 W4 | Mar 2026 W1 | ✓ Done | bar: Feb 2026 W4 to Mar 2026 W1
2.4 UI/UX wireframes & design system | Mar 2026 W1 | Mar 2026 W1 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
2.5 Database schema design (Prisma v6) | Mar 2026 W1 | Mar 2026 W2 | ✓ Done | bar: Mar 2026 W1 to Mar 2026 W2
3. RAD Cycle 1 — Core Infrastructure | Mar 2026 W3 | Mar 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
3.1 Project scaffold (React 18 + Vite + Express) | Mar 2026 W3 | Mar 2026 W3 | ✓ Done | bar: Mar 2026 W3
3.2 Authentication (JWT + Google OAuth) | Mar 2026 W3 | Mar 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
3.3 Email verification & password reset | Mar 2026 W4 | Mar 2026 W4 | ✓ Done | bar: Mar 2026 W4
3.4 School model & multi-school isolation | Mar 2026 W4 | Mar 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
★ Stakeholder Prototype Presentation | Apr 2026 W1 | Apr 2026 W1 | Milestone | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
4. RAD Cycle 2 — LMS Core Modules | Apr 2026 W1 | Apr 2026 W4 | ⟳ Active | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
4.1 Course management (CRUD + enrollment) | Apr 2026 W1 | Apr 2026 W1 | ✓ Done | bar: Apr 2026 W1
4.2 Resource upload (local / Google Drive) | Apr 2026 W1 | Apr 2026 W2 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
4.3 AI quiz generation (Gemini) | Apr 2026 W2 | Apr 2026 W2 | ✓ Done | bar: Apr 2026 W2
4.4 Quiz lifecycle (publish, close, archive) | Apr 2026 W2 | Apr 2026 W3 | ⟳ Active | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
4.5 Student take-quiz + auto-grading | Apr 2026 W3 | Apr 2026 W3 | ⟳ Active | bar: Apr 2026 W3
4.6 Stream tab + announcements | Apr 2026 W3 | Apr 2026 W4 | ⟳ Active | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
4.7 Teacher & student dashboards | Apr 2026 W4 | Apr 2026 W4 | ⟳ Active | bar: Apr 2026 W4
5. RAD Cycle 3 — Advanced Features | May 2026 W1 | May 2026 W3 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
5.1 Remediation module (auto-generate quiz) | May 2026 W1 | May 2026 W1 | ○ Planned | bar: May 2026 W1
5.2 Soft lock & mastery progression system | May 2026 W1 | May 2026 W1 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
5.3 DepEd grading engine (WW / PT / QA) | May 2026 W1 | May 2026 W2 | ○ Planned | bar: May 2026 W1 to May 2026 W2
5.4 Gradebook + CSV export (DepEd format) | May 2026 W2 | May 2026 W3 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
5.5 Admin user management panel | May 2026 W2 | May 2026 W3 | ○ Planned | bar: May 2026 W2 to May 2026 W3
6. Testing & Quality Assurance | May 2026 W4 | Jun 2026 W1 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W1; Sep 2026 W1 to Nov 2026 W4
6.1 Unit & integration testing | May 2026 W4 | Jun 2026 W1 | ○ Planned | bar: May 2026 W4 to Jun 2026 W1
6.2 User Acceptance Testing w/ teachers | May 2026 W4 | Jun 2026 W1 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W1; Sep 2026 W1 to Nov 2026 W4
6.3 Bug fixing & performance optimization | May 2026 W4 | Jun 2026 W1 | ○ Planned | bar: May 2026 W4 to Jun 2026 W1
6.4 ISO 25010 quality evaluation | May 2026 W4 | Jun 2026 W1 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W2; Sep 2026 W1 to Nov 2026 W4
7. Deployment & Live Use | Jun 2026 W1 | Jun 2026 W2 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W2; Sep 2026 W1 to Nov 2026 W4
7.1 Production build, VPS setup & SSL config | Jun 2026 W1 | Jun 2026 W1 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W2; Sep 2026 W1 to Nov 2026 W4
7.2 Deploy to School A & School B | Jun 2026 W2 | Jun 2026 W2 | ○ Planned | bar: Jun 2026 W2
★ Target Deployment — June 2026 | Jun 2026 W3 | Jun 2026 W4 | Milestone | bar: Feb 2026 W1 to May 2026 W4; Jun 2026 W3 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
7.3 Beneficiary onboarding & guided use | Jun 2026 W3 | Jun 2026 W4 | ○ Planned | bar: Jun 2026 W3 to Jun 2026 W4
7.4 Feedback & survey collection | Jun 2026 W3 | Jun 2026 W4 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
7.5 Post-deployment monitoring & patching | Jun 2026 W3 | Jun 2026 W4 | ○ Planned | bar: Jun 2026 W3 to Jun 2026 W4
— Summer Break (July – August 2026) —
Feb – November 2026
8. Documentation — Full Thesis Write-Up | FEB 2026 W1 | Nov 2026 W4 | ⟳ Active | bar: Feb 2026 W1 to Apr 2026 W4; Jun 2026 W4; Sep 2026 W3 to Nov 2026 W4
8.1 Chapter 1 – Introduction | Feb 2026 W1 | Feb 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Feb 2026 W4
8.2 Chapter 2 – Review of Related Literature | March 2026 W1 | March 2026 W4 | ✓ Done | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W3 to Nov 2026 W4
8.3 Chapter 3 – Research Methodology | April 2026 W1 | April 2026 W4 | ⟳ Active | bar: Apr 2026 W1 to Apr 2026 W4
8.4 Chapter 4 – Results & Discussion | Sep 2026 W3 | Oct 2026 W4 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
8.5 Chapter 5 – Conclusion & Recommendations | Oct 2026 W3 | Nov 2026 W2 | ○ Planned | bar: Oct 2026 W3 to Nov 2026 W2
8.6 Abstract, Bibliography & Appendices | Nov 2026 W1 | Nov 2026 W2 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
8.7 Panel review & revisions | Nov 2026 W3 | Nov 2026 W4 | ○ Planned | bar: Nov 2026 W3 to Nov 2026 W4
9. System Finalization & Defense Preparation | Sep 2026 W1 | Nov 2026 W4 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
9.1 Final system polish & UI refinements | Sep 2026 W1 | Sep 2026 W4 | ○ Planned | bar: Sep 2026 W1 to Sep 2026 W4
9.2 Incorporate beneficiary feedback | Sep 2026 W3 | Oct 2026 W4 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
9.3 Final testing & performance benchmarks | Sep 2026 W3 | Oct 2026 W2 | ○ Planned | bar: Sep 2026 W3 to Oct 2026 W2
9.4 System demo preparation & slides | Oct 2026 W3 | Nov 2026 W2 | ○ Planned | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
9.5 Defense rehearsal & mock presentation | Nov 2026 W3 | Nov 2026 W4 | ○ Planned | bar: Nov 2026 W3 to Nov 2026 W4
★ Final Defense — November 2026 | Nov 2026 W3 | Nov 2026 W4 | Milestone | bar: Feb 2026 W1 to Jun 2026 W4; Sep 2026 W1 to Nov 2026 W4
Legend: | ✓ Done | ⟳ Active | ○ Planned | Feb 2026 W1: ● Docs; Feb 2026 W2: ★ Milestone