## AIMS Gantt Chart v2
A.I.M.S. (Automated Intervention and Mastery System): A Web-Based Educational Platform with AI-Driven Assessment and Dynamic Remediation
MONTHS |  |  |  | Start Date | End Date | Assigned to | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
WEEKS | [6 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Requirements Planning (Completed)
| Team Formation & Initial Setup |  |  | 02/02/2026 | 02/02/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Establish team roles and communication channels
| Brainstorming & Title Formulation |  |  | 02/10/2026 | 02/23/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Define clear project scope aligned with DepEd needs
| Title Proposal Submission & Title Defense |  |  | 02/23/2026 | 02/23/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Secure panel approval for AI-powered LMS concept
Phase 2: User Design & Data Gathering (Completed)
| Drafting and Submission of Chapter 1 |  |  | 03/02/2026 | 03/19/2026 | Zambra
↳ Objective: Document problem statement, objectives & significance
| Initial Client Meeting (HNHS) & Adviser Acceptance |  |  | 03/10/2026 | 03/11/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Validate teacher pain points and system requirements
| Adviser/Instructor Meeting (Scope & Primary Draft Clarification) |  |  | 03/17/2026 | 03/17/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Align system features with adviser expectations
| Drafting and Submission of Chapter 2 (RRL) |  |  | 03/27/2026 | 03/30/2026 | Orbigoso, Sagum
↳ Objective: Establish literature foundation for 5 core modules
| Initial UI/UX Wireframing & Database Design |  |  | 03/16/2026 | 04/06/2026 | Sagum
↳ Objective: Produce clickable prototype for stakeholder review
| Formal Presentation of Objectives & Requirements Interview (HNHS) |  |  | 04/06/2026 | 04/06/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Collect interview data for Chapter 3 methodology
Phase 3: Rapid Construction (Active: April – June)
| System Database & Backend Logic Setup |  |  | 04/07/2026 | 04/13/2026 | Sagum
↳ Objective: Implement Prisma schema with user/course/quiz models
| Infrastructure Research & Budget Finalization |  |  | 04/13/2026 | 04/30/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Secure VPS hosting & finalize cost breakdown
| Core Module Development: Digital Library & Course Management |  |  | 04/14/2026 | 04/21/2026 | Sagum
↳ Objective: Enable teachers to upload, organize, and distribute modules
| Core Module Development: AI Quiz Generator (Gemini API) |  |  | 04/21/2026 | 05/05/2026 | Sagum
↳ Objective: Auto-generate quiz items from uploaded PDFs/Word files
| Core Module Development: Automated Grading & Rubric System |  |  | 05/05/2026 | 05/12/2026 | Sagum
↳ Objective: Compute scores instantly using teacher-defined rubrics
| 50-70% System Presentation |  |  | 05/13/2026 | 05/15/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Demonstrate functional Quiz Gen + Auto-Grading to panel
| Writing Chapter 3 (Methodology) |  |  | 05/16/2026 | 05/31/2026 | Orbigoso, Zambra
↳ Objective: Document RAD model, data gathering, and ISO 25010 plan
| Core Module Development: Mastery-Lock & Remediation System |  |  | 05/16/2026 | 05/25/2026 | Sagum
↳ Objective: Enforce conditional progression (fail = locked)
| Core Module Development: Teacher Dashboard & Analytics |  |  | 05/25/2026 | 06/10/2026 | Sagum
↳ Objective: Display real-time student scores, fails, and retake status
| Cross-System Integration: Partner Scheduling & Class Record APIs |  |  | 06/05/2026 | 06/15/2026 | Sagum
↳ Objective: Auto-fetch enrollment & push partial grades to ECR
| Internal System Refinement & Bug Fixing |  |  | 06/16/2026 | 06/23/2026 | Sagum
↳ Objective: Resolve critical bugs and optimize API response times
| 100% System Presentation & Live Web Deployment |  |  | 06/24/2026 | 06/30/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Deploy production-ready system to HNHS beneficiaries
Phase 4: Testing & Evaluation (July – August)
| Alpha Testing (Internal Team) |  |  | 07/01/2026 | 07/15/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Identify and log all functional issues pre-release
| Beta Testing (HNHS Teachers & Students) |  |  | 07/16/2026 | 07/31/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Collect real-user feedback on usability and performance
| ISO 25010 Evaluation Survey Deployment |  |  | 08/01/2026 | 08/15/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Evaluate system quality across all 8 ISO characteristics
| Statistical Analysis of Evaluation Results |  |  | 08/16/2026 | 08/31/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Compute mean scores, standard deviation, and interpret data
Phase 5: Final Documentation & Cutover (September – November)
| Writing Chapter 4 (Results & Discussion) |  |  | 09/01/2026 | 09/30/2026 | Orbigoso, Zambra
↳ Objective: Present and analyze ISO 25010 evaluation findings
| Writing Chapter 5 (Conclusion & Recommendations) |  |  | 10/01/2026 | 10/31/2026 | Orbigoso, Zambra
↳ Objective: Summarize contributions and propose future enhancements
| Final Capstone Defense |  |  | 11/01/2026 | 11/15/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Successfully defend the completed capstone project
| Post-Defense Revisions, Hardbinding & System Turnover |  |  | 11/16/2026 | 11/30/2026 | Orbigoso, Sagum, Zambra
↳ Objective: Finalize manuscript and transfer system ownership to HNHS
Cost Planning:
Location / Phase |  | Expense Description | Quantity |  | Unit Cost (PHP) | Total Cost (PHP) | February W1: Expense Category; March W4: Cost Per Member (3 Members)
Hinigaran (Past - 1 Trip) |  | Transportation (Fuel Contribution) | 3 contributions |  | 150 | 450 | February W1: Transportation; March W4: 150
Hinigaran (Past - 1 Trip) |  | Pocket Money | 3 members |  | 200 | 600 | February W1: Pocket Money; March W4: 200
Hinigaran (Future - 4 Trips) |  | Transportation (Commute) | 12 individual trips (3x4) |  | 240 | 2880 | February W1: Transportation; March W4: 960
Hinigaran (Future - 4 Trips) |  | Pocket Money | 12 individual trips (3x4) |  | 200 | 2400 | February W1: Pocket Money; March W4: 800
System Hosting (6 Months) |  | VPS Subscription (Shared with 16 groups) | 6 months |  | 334 | 2004 | February W1: Hosting; March W4: 125.25
Gemini API |  | Google Gemini API Credits (Estimated) | 6 months |  | 500 | 3000 | February W1: AI API; March W4: 1000
Domain Name |  | Annual Domain Registration (.com) | 1 year |  | 600 | 600 | February W1: Domain; March W4: 200
Printing & Documentation |  | Chapter Drafts, Surveys, Final Manuscript | Estimate |  | 1000 | 1000 | February W1: Documentation; March W4: 333.33
GRAND TOTAL | [5 empty] | 12934 | March W4: Approx. PHP 3,768.58 per member